## Source Data
Entity | Data Object ID | Workstream | Module | Data Object | Object Category | Source Type | Status - Transform | Status - Preload | Status - Load | Status - Postload | Overall status | Data Profiling | Data Mapping | Build | Profiling Planned | Profiling Completed | Mapping Planned | Mapping Completed | Build Planned | Build Completed | Load Planned | Load Completed
Fertil | EAM_MD_003 | EAM | EAM | Equipment | Master Data | Extraction | Complete | Complete | Complete | Complete | Postload Validated | 100 | 75 | 89 | 2025-03-31 | 2025-04-03 | 2025-04-01 | 2025-04-01 | 2025-05-01 | 2025-05-03 | 2025-06-01 | 2025-06-01
Fertil | EAM_MD_005 | EAM | EAM | Equipment BOM | Master Data | Extraction | Complete | Complete | Complete | Complete | Postload Validated | 100 | 75 | 89 | 2025-03-31 | 2025-04-03 | 2025-04-01 | 2025-04-01 | 2025-05-01 | 2025-05-03 | 2025-06-01 | 2025-06-01
Fertil | EAM_MD_002 | EAM | EAM | Functional Location | Master Data | Extraction | Complete | Complete | Complete | Complete | Postload Validated | 100 | 75 | 89 | 2025-03-31 | 2025-04-03 | 2025-04-01 | 2025-04-03 | 2025-05-01 | 2025-05-03 | 2025-06-01 | 2025-06-05
Fertil | EAM_MD_008 | EAM | EAM | Maintenance Plan | Master Data | Extraction | Complete | Complete | Complete | Complete | Postload Validated | 100 | 75 | 89 | 2025-04-03 | 2025-04-03 | 2025-04-01 | 2025-04-03 | 2025-05-01 | 2025-05-01 | 2025-06-03 | 2025-06-05
Fertil | EAM_Trx_020 | EAM | EAM | Open PM Notifications | Transaction Data | Extraction | Complete | Complete | Complete | Complete | Postload Validated | 100 | 75 | 89 | 2025-04-14 | 2025-04-14 | 2025-04-06 | 2025-04-09 | 2025-05-01 | 2025-05-01 | 2025-06-03 | 2025-06-05
Fertil | EAM_Trx_021 | EAM | EAM | Open PM Work Orders | Transaction Data | Extraction | Complete | Complete | Complete | Complete | Postload Validated | 100 | 75 | 89 | 2025-04-14 | 2025-04-17 | 2025-04-06 | 2025-04-09 | 2025-05-07 | 2025-05-10 | 2025-06-03 | 2025-06-05
Fertil | EAM_MD_006 | EAM | EAM | PM Task List | Master Data | Extraction | Complete | Complete | Complete | Complete | Postload Validated | 100 | 75 | 89 | 2025-04-03 | 2025-04-03 | 2025-04-06 | 2025-04-09 | 2025-05-07 | 2025-05-10 | 2025-06-03 | 2025-06-05
Fertil | EAM_MD_001 | EAM | EAM | PM Work Center | Master Data | Construction | Complete | Complete | Complete | Complete | Postload Validated | 100 | 75 | 89 | 2025-03-31 | 2025-03-31 | 2025-04-06 | 2025-04-11 | 2025-05-07 | 2025-05-10 | 2025-06-03 | 2025-06-05
Fertil | FIN_Trx_025 | FIN | TRM | Bank Balances | Transaction Data | Construction | Complete | Complete | Complete | Complete | Postload Validated | 100 | 60 | 87 | 2025-04-14 | 2025-04-17 | 2025-04-06 | 2025-04-11 | 2025-05-07 | 2025-05-10 | 2025-06-01 | 2025-06-06
Fertil | FIN_MD_001 | FIN | TRM | Bank Master | Master Data | Both | Complete | Complete | Complete | Complete | Postload Validated | 100 | 65 | 67 | 2025-03-31 | 2025-03-31 | 2025-04-01 | 2025-04-09 | 2025-05-07 | 2025-05-10 | 2025-06-01 | 2025-06-06
Fertil | FIN_MD_003 | FIN | CO | Cost Center | Critical Data | Construction | Complete | Complete | Complete | Complete | Postload Validated | 100 | 75 | 89 | 2025-03-31 | 2025-03-31 | 2025-04-01 | 2025-04-11 | 2025-05-07 | 2025-05-07 | 2025-06-01 | 2025-06-06
Fertil | FIN_Trx_024 | FIN | FI | Fixed Asset Balances | Transaction Data | Extraction | Complete | Complete | Complete | Delay | Postload Delayed | 100 | 75 | 89 | 2025-04-17 | 2025-04-17 | 2025-04-01 | 2025-04-11 | 2025-05-07 | 2025-05-07 | 2025-06-07 | 2025-06-09
Fertil | FIN_MD_011 | FIN | FI | Fixed Asset Master | Transaction Data | Extraction | Complete | Complete | Complete | Delay | Postload Delayed | 100 | 75 | 89 | 2025-04-17 | 2025-04-17 | 2025-04-01 | 2025-04-09 | 2025-05-07 | 2025-05-07 | 2025-06-07 | 2025-06-09
Fertil | FIN_MD_004 | FIN | FI | GL Account | Critical Data | Construction | Complete | Complete | Complete | Complete | Postload Validated | 100 | 75 | 89 | 2025-03-31 | 2025-03-31 | 2025-04-01 | 2025-04-11 | 2025-05-01 | 2025-05-10 | 2025-06-07 | 2025-06-09
Fertil | FIN_Trx_028 | FIN | FI | GL Balances | Transaction Data | Extraction | Complete | Complete | Delay | Not started | Load Delayed | 100 | 75 | 89 | 2025-04-17 | 2025-04-17 | 2025-04-06 | 2025-04-11 | 2025-05-01 | 2025-05-10 | 2025-06-07 | 2025-06-09
Fertil | FIN_Trx_022 | FIN | FI | Open Accounts Payable | Transaction Data | Extraction | Complete | Complete | Delay | Not started | Load Delayed | 100 | 75 | 89 | 2025-04-17 | 2025-04-17 | 2025-04-06 | 2025-04-11 | 2025-05-01 | 2025-05-10 | 2025-06-01 | 2025-06-09
Fertil | FIN_Trx_023 | FIN | FI | Open Accounts Receivable | Transaction Data | Extraction | Complete | Complete | Complete | In progress | Postload In Progress | 100 | 75 | 89 | 2025-04-14 | 2025-04-17 | 2025-04-06 | 2025-04-09 | 2025-05-01 | 2025-05-15 | 2025-06-01 | 2025-06-09
Fertil | FIN_MD_008 | FIN | PPM | PPM Item | Master Data | Construction | Complete | Complete | Complete | Complete | Postload Validated | 100 | 75 | 89 | 2025-04-18 | 2025-04-18 | 2025-04-06 | 2025-04-09 | 2025-05-01 | 2025-05-15 | 2025-06-01 | 2025-06-09
Fertil | FIN_MD_002 | FIN | CO | Profit Center | Critical Data | Construction | Complete | Complete | Complete | Complete | Postload Validated | 100 | 75 | 89 | 2025-04-14 | 2025-04-17 | 2025-04-06 | 2025-04-09 | 2025-05-15 | 2025-05-15 | 2025-06-03 | 2025-06-10
Fertil | FIN_MD_009 | FIN | PS | Project | Master Data | Construction | Complete | Complete | Complete | Complete | Postload Validated | 100 | 75 | 89 | 2025-03-31 | 2025-03-31 | 2025-04-01 | 2025-04-11 | 2025-05-15 | 2025-05-15 | 2025-06-03 | 2025-06-10
Fertil | FIN_Trx_027 | FIN | TRM | TRM Bank Guarantee | Transaction Data | Construction | Complete | Complete | Delay | Not started | Load Delayed | 100 | 75 | 89 | 2025-04-14 | 2025-04-17 | 2025-04-01 | 2025-04-11 | 2025-05-15 | 2025-05-15 | 2025-06-03 | 2025-06-10
Fertil | FIN_MD_005 | FIN | TRM | TRM BP - Treasury Fields | Master Data | Construction | Complete | Complete | Complete | Complete | Postload Validated | 100 | 75 | 89 | 2025-04-03 | 2025-04-03 | 2025-04-01 | 2025-04-09 | 2025-05-15 | 2025-05-15 | 2025-06-03 | 2025-06-10
Fertil | FIN_Trx_020 | FIN | PS | WBS Budget | Transaction Data | Construction | Complete | Complete | Complete | Complete | Postload Validated | 100 | 75 | 89 | 2025-04-17 | 2025-04-17 | 2025-04-01 | 2025-04-11 | 2025-05-15 | 2025-05-15 | 2025-06-03 | 2025-06-10
Fertil | FIN_MD_010 | FIN | PS | WBS Elements | Master Data | Construction | Complete | Complete | Complete | Complete | Postload Validated | 100 | 75 | 89 | 2025-04-03 | 2025-04-03 | 2025-04-01 | 2025-04-11 | 2025-05-15 | 2025-05-15 | 2025-06-03 | 2025-06-10
Fertil | HCM_MD_051 | HCM | EC | Accommodation Status_Fertil | Master Data | Extraction | Complete | Complete | Complete | Complete | Postload Validated | 100 | 100 | 100 | 2025-04-03 | 2025-04-03 | 2025-04-06 | 2025-04-09 | 2025-05-15 | 2025-05-15 | 2025-06-01 | 2025-06-10
Fertil | HCM_Trx_034 | HCM | PY | Advance Claims | Transaction Data | Extraction | Complete | Complete | Delay | Not started | Load Delayed | 100 | 100 | 67 | 2025-04-20 | 2025-04-20 | 2025-04-06 | 2025-04-11 | 2025-05-15 | 2025-05-15 | 2025-06-01 | 2025-06-10
Fertil | HCM_MD_036 | HCM | EP | Background data elements | Master Data | Extraction | Complete | Complete | Delay | Not started | Load Delayed | 100 | 90 | 75 | 2025-04-07 | 2025-04-07 | 2025-04-06 | 2025-04-11 | 2025-05-15 | 2025-05-15 | 2025-06-01 | 2025-06-10
Fertil | HCM_MD_010 | HCM | FO | Bank Master | Master Data | Extraction | Complete | Complete | Complete | Complete | Postload Validated | 100 | 56 | 65 | 2025-03-31 | 2025-03-31 | 2025-04-06 | 2025-04-09 | 2025-05-15 | 2025-05-15 | 2025-06-07 | 2025-06-10
Fertil | HCM_Trx_035 | HCM | PY | Benefit Claims | Transaction Data | Extraction | Complete | Complete | Delay | Not started | Load Delayed | 100 | 76 | 100 | 2025-04-17 | 2025-04-17 | 2025-04-06 | 2025-04-09 | 2025-05-01 | 2025-05-08 | 2025-06-07 | 2025-06-11
Fertil | HCM_MD_026 | HCM | EC | Benefit Enrolment | Master Data | Extraction | Complete | Complete | Complete | Complete | Postload Validated | 100 | 54 | 34 | 2025-03-31 | 2025-03-31 | 2025-04-06 | 2025-04-09 | 2025-05-01 | 2025-05-08 | 2025-06-07 | 2025-06-11
Fertil | HCM_MD_002 | HCM | FO | Business Unit | Master Data | Extraction | Complete | Complete | Complete | Complete | Postload Validated | 100 | 75 | 89 | 2025-03-31 | 2025-03-31 | 2025-04-01 | 2025-04-11 | 2025-05-01 | 2025-05-08 | 2025-06-07 | 2025-06-11
Fertil | HCM_MD_001 | HCM | FO | CEO Office | Master Data | Extraction | Complete | Complete | Complete | Complete | Postload Validated | 100 | 75 | 89 | 2025-04-07 | 2025-04-17 | 2025-04-01 | 2025-04-11 | 2025-05-01 | 2025-05-08 | 2025-06-07 | 2025-06-11
Fertil | HCM_MD_004 | HCM | FO | Departments | Master Data | Extraction | Complete | Complete | Complete | Complete | Postload Validated | 100 | 75 | 89 | 2025-04-07 | 2025-04-17 | 2025-04-01 | 2025-04-11 | 2025-05-01 | 2025-05-08 | 2025-06-07 | 2025-06-11
Fertil | HCM_MD_046 | HCM | EC | Disciplinary Action_Fertil | Master Data | Extraction | Complete | Complete | Complete | Complete | Postload Validated | 100 | 75 | 89 | 2025-04-03 | 2025-04-03 | 2025-04-01 | 2025-04-09 | 2025-05-07 | 2025-05-08 | 2025-06-01 | 2025-06-11
Fertil | HCM_MD_003 | HCM | FO | Division | Master Data | Extraction | Complete | Complete | Complete | Complete | Postload Validated | 100 | 75 | 89 | 2025-04-03 | 2025-04-03 | 2025-04-01 | 2025-04-09 | 2025-05-07 | 2025-05-08 | 2025-06-01 | 2025-06-11
Fertil | HCM_Trx_056 | HCM | TM | Employee Absence Quota | Transaction Data | Extraction | Complete | Complete | Complete | In progress | Postload In Progress | 100 | 75 | 89 | 2025-04-14 | 2025-04-14 | 2025-04-06 | 2025-04-11 | 2025-05-07 | 2025-05-08 | 2025-06-01 | 2025-06-11
Fertil | HCM_Trx_055 | HCM | TM | Employee Absences | Transaction Data | Extraction | Complete | Complete | Complete | In progress | Postload In Progress | 100 | 75 | 89 | 2025-04-17 | 2025-04-17 | 2025-04-06 | 2025-04-11 | 2025-05-07 | 2025-05-08 | 2025-06-07 | 2025-06-11
Fertil | HCM_MD_015 | HCM | EC | Employee Addresses | Master Data | Extraction | Complete | Complete | Complete | Complete | Postload Validated | 100 | 75 | 89 | 2025-04-07 | 2025-04-07 | 2025-04-06 | 2025-04-11 | 2025-05-07 | 2025-05-08 | 2025-06-07 | 2025-06-11
Fertil | HCM_MD_011 | HCM | EC | Employee Basic UDF | Master Data | Extraction | Complete | Complete | Complete | Complete | Postload Validated | 100 | 75 | 89 | 2025-03-31 | 2025-03-31 | 2025-04-06 | 2025-04-11 | 2025-05-07 | 2025-05-08 | 2025-06-07 | 2025-06-12
Fertil | HCM_Trx_057 | HCM | TM | Employee Attendance | Transaction Data | Extraction | Complete | Complete | Complete | In progress | Postload In Progress | 100 | 75 | 89 | 2025-04-17 | 2025-04-17 | 2025-04-06 | 2025-04-11 | 2025-05-07 | 2025-05-07 | 2025-06-07 | 2025-06-12
Fertil | HCM_MD_012 | HCM | EC | Employee Biographical Info | Master Data | Extraction | Complete | Complete | Complete | Complete | Postload Validated | 100 | 75 | 89 | 2025-03-31 | 2025-04-17 | 2025-04-09 | 2025-04-11 | 2025-05-07 | 2025-05-07 | 2025-06-01 | 2025-06-12
Fertil | HCM_MD_028 | HCM | EC | Employee Compensation | Master Data | Extraction | Complete | Complete | Complete | Complete | Postload Validated | 100 | 75 | 89 | 2025-03-31 | 2025-04-17 | 2025-04-01 | 2025-04-09 | 2025-05-01 | 2025-05-01 | 2025-06-01 | 2025-06-12
Fertil | HCM_MD_020 | HCM | EC | Employee Dependents | Master Data | Extraction | Complete | Complete | Complete | Complete | Postload Validated | 100 | 75 | 89 | 2025-04-07 | 2025-04-17 | 2025-04-01 | 2025-04-09 | 2025-05-01 | 2025-05-01 | 2025-06-01 | 2025-06-12
Fertil | HCM_MD_053 | HCM | EC | Employee Documents | Master Data | Extraction | Complete | Complete | Complete | Complete | Postload Validated | 100 | 75 | 89 | 2025-04-07 | 2025-04-07 | 2025-04-01 | 2025-04-11 | 2025-05-01 | 2025-05-01 | 2025-06-10 | 2025-06-12
Fertil | HCM_MD_016 | HCM | EC | Employee Email | Master Data | Extraction | Complete | Complete | Complete | Complete | Postload Validated | 100 | 75 | 89 | 2025-04-07 | 2025-04-07 | 2025-04-01 | 2025-04-11 | 2025-05-01 | 2025-05-01 | 2025-06-10 | 2025-06-12
Fertil | HCM_MD_014 | HCM | EC | Employee Employment Info | Master Data | Extraction | Complete | Complete | Complete | Complete | Postload Validated | 100 | 75 | 89 | 2025-04-03 | 2025-04-17 | 2025-04-01 | 2025-04-11 | 2025-05-01 | 2025-05-01 | 2025-06-10 | 2025-06-12
Fertil | HCM_MD_019 | HCM | EC | Employee Global Info | Master Data | Extraction | Complete | Complete | Complete | Complete | Postload Validated | 100 | 75 | 89 | 2025-04-03 | 2025-04-17 | 2025-04-06 | 2025-04-11 | 2025-05-07 | 2025-05-07 | 2025-06-10 | 2025-06-12
Fertil | HCM_MD_024 | HCM | EC | Employee Job Information | Master Data | Extraction | Complete | Complete | Complete | Complete | Postload Validated | 100 | 75 | 89 | 2025-04-03 | 2025-04-03 | 2025-04-06 | 2025-04-11 | 2025-05-07 | 2025-05-07 | 2025-06-10 | 2025-06-12
Fertil | HCM_MD_021 | HCM | EC | Employee National ID | Master Data | Extraction | Complete | Complete | Complete | Complete | Postload Validated | 100 | 75 | 89 | 2025-04-07 | 2025-04-07 | 2025-04-06 | 2025-04-11 | 2025-05-07 | 2025-05-13 | 2025-06-10 | 2025-06-13
Fertil | HCM_MD_027 | HCM | EC | Employee Payment Info | Master Data | Extraction | Complete | Complete | Complete | Complete | Postload Validated | 100 | 75 | 89 | 2025-03-31 | 2025-03-31 | 2025-04-06 | 2025-04-11 | 2025-05-07 | 2025-05-13 | 2025-06-10 | 2025-06-13
Fertil | HCM_Trx_061 | HCM | TM | Employee Permissions | Transaction Data | Extraction | Complete | Complete | Delay | Not started | Load Delayed | 100 | 75 | 89 | 2025-04-14 | 2025-04-14 | 2025-04-06 | 2025-04-09 | 2025-05-07 | 2025-05-13 | 2025-06-10 | 2025-06-13
Fertil | HCM_MD_013 | HCM | EC | Employee Personal Info | Critical Data | Extraction | Complete | Complete | Complete | Complete | Postload Validated | 100 | 75 | 89 | 2025-04-14 | 2025-04-14 | 2025-04-09 | 2025-04-09 | 2025-05-07 | 2025-05-13 | 2025-06-10 | 2025-06-13
Fertil | HCM_MD_017 | HCM | EC | Employee Phone | Master Data | Extraction | Complete | Complete | Complete | Complete | Postload Validated | 100 | 75 | 89 | 2025-03-31 | 2025-03-31 | 2025-04-09 | 2025-04-13 | 2025-05-07 | 2025-05-13 | 2025-06-01 | 2025-06-13
Fertil | HCM_Trx_060 | HCM | TM | Employee Quota Correction | Transaction Data | Extraction | Complete | Complete | Complete | In progress | Postload In Progress | 100 | 75 | 89 | 2025-04-14 | 2025-04-14 | 2025-04-01 | 2025-04-13 | 2025-05-07 | 2025-05-13 | 2025-06-01 | 2025-06-13
Fertil | HCM_Trx_062 | HCM | TM | Employee Remuneration | Transaction Data | Extraction | Complete | Complete | Complete | In progress | Postload In Progress | 100 | 75 | 89 | 2025-04-14 | 2025-04-14 | 2025-04-01 | 2025-04-13 | 2025-05-07 | 2025-05-13 | 2025-06-01 | 2025-06-13
Fertil | HCM_Trx_058 | HCM | TM | Employee Substitution | Transaction Data | Extraction | Complete | Complete | Complete | In progress | Postload In Progress | 100 | 75 | 89 | 2025-04-17 | 2025-04-17 | 2025-04-01 | 2025-04-13 | 2025-05-01 | 2025-05-13 | 2025-06-10 | 2025-06-13
Fertil | HCM_Trx_059 | HCM | TM | Employee Time Transfer Specification | Transaction Data | Extraction | Complete | Complete | Complete | Complete | Postload Validated | 100 | 75 | 89 | 2025-04-17 | 2025-04-17 | 2025-04-01 | 2025-04-13 | 2025-05-01 | 2025-05-13 | 2025-06-10 | 2025-06-13
Fertil | HCM_MD_022 | HCM | EC | Employee Work Permits | Master Data | Extraction | Complete | Complete | Complete | Complete | Postload Validated | 100 | 75 | 89 | 2025-03-31 | 2025-03-31 | 2025-04-01 | 2025-04-13 | 2025-05-01 | 2025-05-13 | 2025-06-10 | 2025-06-13
Fertil | HCM_MD_047 | HCM | EC | Housing Declaration_Fertil | Master Data | Extraction | Complete | Complete | Complete | Complete | Postload Validated | 100 | 75 | 89 | 2025-04-07 | 2025-04-07 | 2025-04-06 | 2025-04-13 | 2025-05-01 | 2025-05-13 | 2025-06-10 | 2025-06-13
Fertil | HCM_MD_052 | HCM | EC | Housing Master_Fertil | Master Data | Extraction | Complete | Complete | Complete | Complete | Postload Validated | 100 | 75 | 89 | 2025-04-07 | 2025-04-07 | 2025-04-06 | 2025-04-09 | 2025-05-01 | 2025-05-13 | 2025-06-10 | 2025-06-13
Fertil | HCM_MD_048 | HCM | EC | Housing Request_Fertil | Master Data | Extraction | Complete | Complete | Complete | Complete | Postload Validated | 100 | 75 | 89 | 2025-04-03 | 2025-04-03 | 2025-04-06 | 2025-04-09 | 2025-05-15 | 2025-05-15 | 2025-06-01 | 2025-06-13
Fertil | HCM_MD_008 | HCM | FO | Job Classification | Master Data | Extraction | Complete | Complete | Complete | Complete | Postload Validated | 100 | 75 | 89 | 2025-04-03 | 2025-04-03 | 2025-04-06 | 2025-04-13 | 2025-05-15 | 2025-05-15 | 2025-06-01 | 2025-06-13
Fertil | HCM_MD_006 | HCM | FO | Job Function | Master Data | Extraction | Complete | Complete | Complete | Complete | Postload Validated | 100 | 75 | 89 | 2025-03-31 | 2025-03-31 | 2025-04-06 | 2025-04-13 | 2025-05-15 | 2025-05-15 | 2025-06-01 | 2025-06-13
Fertil | HCM_MD_007 | HCM | FO | Job Sub-Function | Master Data | Extraction | Complete | Complete | Complete | Complete | Postload Validated | 100 | 75 | 89 | 2025-03-31 | 2025-04-21 | 2025-04-06 | 2025-04-13 | 2025-05-15 | 2025-05-15 | 2025-06-03 | 2025-06-14
Fertil | HCM_Trx_032 | HCM | PY | One time deduction | Transaction Data | Extraction | Complete | Complete | Complete | Complete | Postload Validated | 100 | 75 | 89 | 2025-04-17 | 2025-04-21 | 2025-04-06 | 2025-04-13 | 2025-05-15 | 2025-05-15 | 2025-06-13 | 2025-06-14
Fertil | HCM_MD_049 | HCM | EC | Part Time Study_Fertil | Master Data | Extraction | Complete | Complete | Complete | Complete | Postload Validated | 100 | 75 | 89 | 2025-03-31 | 2025-03-31 | 2025-04-06 | 2025-04-13 | 2025-05-15 | 2025-05-15 | 2025-06-13 | 2025-06-14
Fertil | HCM_Trx_030 | HCM | PY | Pay Component Non-Recurring | Transaction Data | Extraction | Complete | Complete | Complete | Complete | Postload Validated | 100 | 75 | 89 | 2025-04-17 | 2025-04-17 | 2025-04-06 | 2025-04-13 | 2025-05-15 | 2025-05-15 | 2025-06-13 | 2025-06-14
Fertil | HCM_MD_029 | HCM | PY | Pay Component Recurring | Master Data | Extraction | Complete | Complete | Complete | Complete | Postload Validated | 100 | 75 | 89 | 2025-04-10 | 2025-04-21 | 2025-04-06 | 2025-04-13 | 2025-05-15 | 2025-05-15 | 2025-06-13 | 2025-06-14
Fertil | HCM_MD_009 | HCM | FO | Position | Master Data | Extraction | Complete | Complete | Complete | Complete | Postload Validated | 100 | 75 | 89 | 2025-04-10 | 2025-04-10 | 2025-04-01 | 2025-04-09 | 2025-05-01 | 2025-05-01 | 2025-06-13 | 2025-06-14
Fertil | HCM_Trx_031 | HCM | PY | Recurring deduction | Transaction Data | Extraction | Complete | Complete | Complete | Complete | Postload Validated | 100 | 75 | 89 | 2025-04-14 | 2025-04-14 | 2025-04-01 | 2025-04-09 | 2025-05-01 | 2025-05-13 | 2025-06-01 | 2025-06-14
Fertil | HCM_MD_005 | HCM | FO | Section | Master Data | Extraction | Complete | Complete | Complete | Complete | Postload Validated | 100 | 75 | 89 | 2025-04-03 | 2025-04-03 | 2025-04-01 | 2025-04-13 | 2025-05-01 | 2025-05-13 | 2025-06-01 | 2025-06-14
Fertil | HSE_MD_003 | HSE | HSE | Controls | Master Data | Construction | Complete | Complete | Complete | Complete | Postload Validated | 100 | 75 | 89 | 2025-04-03 | 2025-04-03 | 2025-04-01 | 2025-04-13 | 2025-05-01 | 2025-05-13 | 2025-06-01 | 2025-06-14
Fertil | HSE_MD_007 | HSE | HSE | Jobs | Master Data | Construction | Complete | Complete | Complete | Complete | Postload Validated | 100 | 75 | 89 | 2025-03-31 | 2025-03-31 | 2025-04-06 | 2025-04-09 | 2025-05-01 | 2025-05-13 | 2025-06-13 | 2025-06-14
Fertil | HSE_MD_004 | HSE | HSE | Locations | Master Data | Construction | Complete | Complete | Complete | Complete | Postload Validated | 100 | 75 | 89 | 2025-03-31 | 2025-03-31 | 2025-04-06 | 2025-04-09 | 2025-05-15 | 2025-05-19 | 2025-06-13 | 2025-06-14
Fertil | PPQ_MD_004 | PPQ | PP | Master Recipe | Master Data | Construction | Complete | Complete | Complete | Complete | Postload Validated | 100 | 75 | 89 | 2025-03-31 | 2025-03-31 | 2025-04-06 | 2025-04-13 | 2025-05-15 | 2025-05-19 | 2025-06-13 | 2025-06-14
Fertil | PPQ_MD_003 | PPQ | PP | PP Bill of Materials | Master Data | Construction | Complete | Complete | Complete | Complete | Postload Validated | 100 | 75 | 89 | 2025-04-10 | 2025-04-10 | 2025-04-06 | 2025-04-13 | 2025-05-15 | 2025-05-19 | 2025-06-13 | 2025-06-14
Fertil | PPQ_MD_001 | PPQ | PP | PP Resources | Master Data | Construction | Complete | Complete | Complete | Complete | Postload Validated | 100 | 75 | 89 | 2025-04-10 | 2025-04-10 | 2025-04-06 | 2025-04-13 | 2025-05-15 | 2025-05-15 | 2025-06-13 | 2025-06-14
Fertil | PPQ_MD_005 | PPQ | PP | Production Version | Master Data | Construction | Complete | Complete | Complete | Complete | Postload Validated | 100 | 75 | 89 | 2025-04-03 | 2025-04-17 | 2025-04-06 | 2025-04-13 | 2025-05-15 | 2025-05-15 | 2025-06-13 | 2025-06-14
Fertil | PPQ_MD_009 | PPQ | QM | QM Inspection Characteristic | Master Data | Extraction | Complete | Complete | Complete | Complete | Postload Validated | 100 | 75 | 89 | 2025-04-03 | 2025-04-17 | 2025-04-06 | 2025-04-13 | 2025-05-15 | 2025-05-15 | 2025-06-13 | 2025-06-14
Fertil | PPQ_MD_010 | PPQ | QM | QM Inspection Plan | Master Data | Extraction | Complete | Complete | Complete | Complete | Postload Validated | 100 | 75 | 89 | 2025-04-10 | 2025-04-10 | 2025-04-06 | 2025-04-13 | 2025-05-15 | 2025-05-15 | 2025-06-01 | 2025-06-14
Fertil | PPQ_MD_012 | PPQ | QM | Quality Info Record | Master Data | Extraction | Complete | Complete | Complete | Complete | Postload Validated | 100 | 75 | 89 | 2025-04-10 | 2025-04-21 | 2025-04-06 | 2025-04-09 | 2025-05-01 | 2025-05-01 | 2025-06-01 | 2025-06-17
Fertil | PRC_MD_010 | PRC | PRC | Batch Master | Transaction Data | Extraction | Complete | Complete | Complete | In progress | Postload In Progress | 100 | 65 | 100 | 2025-04-14 | 2025-04-21 | 2025-04-06 | 2025-04-09 | 2025-05-01 | 2025-05-01 | 2025-06-01 | 2025-06-17
Fertil | PRC_MD_004 | PRC | PRC | Business Partner - Vendor Master | Critical Data | Extraction | Complete | Complete | Complete | Complete | Postload Validated | 100 | 75 | 78 | 2025-04-14 | 2025-04-21 | 2025-04-09 | 2025-04-13 | 2025-05-01 | 2025-05-01 | 2025-06-13 | 2025-06-17
Fertil | PRC_MD_001 | PRC | PRC | Class & Characteristics | Master Data | Extraction | Complete | Complete | Complete | Complete | Postload Validated | 100 | 75 | 89 | 2025-04-10 | 2025-04-21 | 2025-04-01 | 2025-04-13 | 2025-05-01 | 2025-05-01 | 2025-06-13 | 2025-06-17
Fertil | PRC_Trx_022 | PRC | IM | Inventory Stock Upload | Transaction Data | Extraction | Complete | Complete | Complete | In progress | Postload In Progress | 100 | 75 | 89 | 2025-04-17 | 2025-04-21 | 2025-04-01 | 2025-04-13 | 2025-05-01 | 2025-05-01 | 2025-06-13 | 2025-06-17
Fertil | PRC_MD_002 | PRC | PRC | Material Master | Critical Data | Extraction | Complete | Complete | Complete | Complete | Postload Validated | 100 | 75 | 89 | 2025-04-17 | 2025-04-21 | 2025-04-01 | 2025-04-13 | 2025-05-20 | 2025-05-20 | 2025-06-13 | 2025-06-17
Fertil | PRC_Trx_020 | PRC | PRC | Open Purchase Contract | Transaction Data | Extraction | Complete | Complete | Delay | Not started | Load Delayed | 100 | 75 | 89 | 2025-04-17 | 2025-04-21 | 2025-04-01 | 2025-04-09 | 2025-05-20 | 2025-05-20 | 2025-06-13 | 2025-06-17
Fertil | PRC_Trx_021 | PRC | PRC | Open Purchase Order | Transaction Data | Extraction | Complete | Complete | Delay | Not started | Load Delayed | 100 | 75 | 89 | 2025-04-17 | 2025-04-21 | 2025-04-01 | 2025-04-09 | 2025-05-20 | 2025-05-20 | 2025-06-13 | 2025-06-17
Fertil | PRC_MD_006 | PRC | PRC | Purchase Info Record | Master Data | Extraction | Complete | Complete | Complete | Complete | Postload Validated | 100 | 75 | 89 | 2025-03-31 | 2025-03-31 | 2025-04-09 | 2025-04-13 | 2025-05-20 | 2025-05-20 | 2025-06-01 | 2025-06-17
Fertil | PRC_Trx_023 | PRC | EWM | Warehouse Stock Upload | Transaction Data | Extraction | Complete | Complete | Delay | Not started | Load Delayed | 100 | 75 | 89 | 2025-04-14 | 2025-04-21 | 2025-04-09 | 2025-04-13 | 2025-05-20 | 2025-05-20 | 2025-06-01 | 2025-06-17
Fertil | PRC_MD_007 | PRC | EWM | WM Bin Master | Master Data | Extraction | Complete | Complete | Complete | Complete | Postload Validated | 100 | 75 | 89 | 2025-03-31 | 2025-04-21 | 2025-04-09 | 2025-04-13 | 2025-05-20 | 2025-05-20 | 2025-06-01 | 2025-06-17
Fertil | PRC_MD_009 | PRC | EWM | WM Product Master | Master Data | Extraction | Complete | Complete | Complete | Complete | Postload Validated | 100 | 75 | 89 | 2025-03-31 | 2025-03-31 | 2025-04-01 | 2025-04-09 | 2025-05-01 | 2025-05-01 | 2025-06-13 | 2025-06-17
Fertil | PRC_MD_008 | PRC | EWM | WM Resource | Master Data | Construction | Complete | Complete | Complete | Complete | Postload Validated | 100 | 75 | 89 | 2025-03-31 | 2025-03-31 | 2025-04-01 | 2025-04-09 | 2025-05-01 | 2025-05-01 | 2025-06-13 | 2025-06-17
Fertil | SSD_MD_001 | SSD | SSD | Business Partner - Customer Master | Critical Data | Extraction | Complete | Complete | Complete | Complete | Postload Validated | 100 | 43 | 56 | 2025-04-14 | 2025-04-21 | 2025-04-01 | 2025-04-13 | 2025-05-01 | 2025-05-01 | 2025-06-13 | 2025-06-17
Fertil | SSD_Trx_021 | SSD | SSD | Open Sales Orders | Transaction Data | Extraction | Complete | Complete | Complete | Complete | Postload Validated | 100 | 75 | 89 | 2025-04-14 | 2025-04-21 | 2025-04-01 | 2025-04-09 | 2025-05-01 | 2025-05-01 | 2025-06-13 | 2025-06-17
Fertil | SSD_MD_003 | SSD | SSD | Sales Pricing Conditions | Master Data | Construction | Complete | Complete | Complete | Complete | Postload Validated | 100 | 75 | 89 | 2025-04-10 | 2025-04-10 | 2025-04-01 | 2025-04-09 | 2025-05-01 | 2025-05-01 | 2025-06-13 | 2025-06-17